Project Plan for the Railway Reservation System

1.Project Overview

| Project Name | Railway Reservation System |
| --- | --- |
| Project Manager | Mr. Sarthak Shewale (Team Lead) |
| Start Date | 10 November 2025 |
| Finish Date (Expected) | 10 February 2026 |
| Project Duration | 3 months (approx. 90 days) |
| Project Objective | To design and develop a computerized railway ticket reservation system that allows passengers to search for trains, check seat availability, make reservations, cancel bookings, and generate tickets online. |

2.Project Tasks and Descriptions

| Task ID | Task Name | Description |
| --- | --- | --- |
| T1 | Requirement Analysis | Identify and document user requirements, system scope, and functional modules. |
| T2 | Feasibility Study | Evaluate technical, operational, and financial feasibility. |
| T3 | System Design | Create architecture diagrams, ER diagrams, and database schema. |
| T4 | Database Setup | Create necessary tables for trains, passengers, tickets, and transactions. |
| T5 | Front-End Development | Design the user interface for booking, inquiry, and cancellation modules. |
| T6 | Back-End Development | Implement server-side logic for ticket booking, seat allocation, and payment handling. |
| T7 | Integration & Testing | Combine all modules and perform unit, integration, and system testing. |
| T8 | Documentation | Prepare user manual, test report, and technical documentation. |
| T9 | Deployment | Deploy the system on a server environment. |
| T10 | Maintenance & Support | Post-deployment issue fixing and updates. |

3.Duration of Each Task

| Task ID | Task Name | Duration (Days) |
| --- | --- | --- |
| T1 | Requirement Analysis | 7 days |
| T2 | Feasibility Study | 5 days |
| T3 | System Design | 10 days |
| T4 | Database Setup | 7 days |
| T5 | Front-End Development | 20 days |
| T6 | Back-End Development | 25 days |
| T7 | Integration & Testing | 10 days |
| T8 | Documentation | 4 days |
| T9 | Deployment | 2 days |
| T10 | Maintenance & Support | Ongoing (post-release) |

4.Project Milestones

| Milestone ID | Milestone Description | Target Date |
| --- | --- | --- |
| M1 | Project Initiation Completed | 15 Nov 2025 |
| M2 | Requirement & Feasibility Approved | 20 Nov 2025 |
| M3 | Design Phase Completed | 05 Dec 2025 |
| M4 | Development Completed | 20 Jan 2026 |
| M5 | Testing & Integration Completed | 01 Feb 2026 |
| M6 | Final Deployment | 10 Feb 2026 |

5. Task Dependencies

| Task | Depends On |
| --- | --- |
| T2 – Feasibility Study | T1 – Requirement Analysis |
| T3 – System Design | T1, T2 |
| T4 – Database Setup | T3 |
| T5 – Front-End Development | T3 |
| T6 – Back-End Development | T3, T4 |
| T7 – Integration & Testing | T5, T6 |
| T8 – Documentation | T7 |
| T9 – Deployment | T7, T8 |
| T10 – Maintenance | T9 |

6. Project Calendar

| Work Days | Monday to Friday |
| --- | --- |
| Working Hours | 9:00 AM – 5:00 PM |
| Holidays | Saturday, Sunday, and Public Holidays |
| Total Working Days per Week | 5 |
| Total Working Hours per Day | 8 |

7. Project Resources

| Resource ID | Resource Name | Type | Role/Responsibility |
| --- | --- | --- | --- |
| R1 | Project Manager | Human | Project planning, monitoring, reporting |
| R2 | System Analyst | Human | Requirement gathering, documentation |
| R3 | UI/UX Designer | Human | Front-end interface design |
| R4 | Software Developer | Human | Backend logic, APIs, integration |
| R5 | Database Administrator | Human | Database creation and maintenance |
| R6 | Tester / QA Engineer | Human | Test planning and execution |
| R7 | Server & Tools | Technical | Hosting environment and IDE tools |
| R8 | Git / Version Control | Software | Source code management |
| R9 | Documentation Tools | Software | Prepare reports and manuals |

8.Resource Allocation

| Task | Assigned Resource(s) |
| --- | --- |
| T1 – Requirement Analysis | Project Manager, System Analyst |
| T2 – Feasibility Study | Project Manager, Analyst |
| T3 – System Design | Analyst, UI/UX Designer |
| T4 – Database Setup | Database Administrator |
| T5 – Front-End Development | UI/UX Designer, Developer |
| T6 – Back-End Development | Developer, DBA |
| T7 – Integration & Testing | Developer, Tester |
| T8 – Documentation | Analyst, Tester |
| T9 – Deployment | Developer, DBA |
| T10 – Maintenance | Developer, Support Staff |

9. Project Baseline

The baseline is established after approval of the plan, including:

- Scope baseline: Defined functional modules.

- Schedule baseline: As per timeline table.

- Cost baseline: Estimated resource cost and tool license.

- Performance baseline: Milestones, quality metrics, and test success criteria.