Execute and Monitor Project Plan for First-Year Engineering Admission System

1.Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | First-Year Engineering Admission System |
| Project Manager | Ms. Riya Patil |
| Start Date | 1 November 2025 |
| Expected Finish Date | 31 January 2026 |
| Current Status Date | 20 December 2025 |
| Overall Progress | ~60% complete |

2. Project Tasks and Current Status

| Task ID | Task Name | Planned Duration (Days) | Actual Duration (Days) | % Complete | Status |
| --- | --- | --- | --- | --- | --- |
| T1 | Requirement Gathering | 7 | 7 | 100% | ✅ Completed |
| T2 | Feasibility Study | 5 | 6 | 100% | ✅ Completed |
| T3 | System Design | 10 | 11 | 100% | ✅ Completed |
| T4 | Database Setup | 8 | 8 | 100% | ✅ Completed |
| T5 | Application Development | 25 | 20 | 80% | 🟡 In Progress |
| T6 | Integration & Testing | 10 | - | 0% | ⏳ Pending |
| T7 | Deployment & Training | 5 | - | 0% | ⏳ Pending |
| T8 | Documentation | 4 | - | 0% | ⏳ Pending |

3. Task Progress Update

| Phase | Planned Start | Planned Finish | Actual Start | Actual Finish / Current | % Complete |
| --- | --- | --- | --- | --- | --- |
| Analysis | 01 Nov | 07 Nov | 01 Nov | 07 Nov | 100% |
| Feasibility | 08 Nov | 12 Nov | 08 Nov | 13 Nov | 100% |
| Design | 13 Nov | 23 Nov | 14 Nov | 25 Nov | 100% |
| Database Setup | 24 Nov | 01 Dec | 24 Nov | 01 Dec | 100% |
| Development | 02 Dec | 26 Dec | 02 Dec | 20 Dec (ongoing) | 80% |
| Testing | 27 Dec | 06 Jan | - | - | 0% |
| Deployment | 07 Jan | 10 Jan | - | - | 0% |
| Documentation | 11 Jan | 14 Jan | - | - | 0% |

4. Planned vs. Actual Progress

| Metric | Planned Value | Actual Value | Variance |
| --- | --- | --- | --- |
| Planned % Completion | 70% | 60% | -10% |
| Planned Days Elapsed | 50 days | 50 days | 0 |
| Planned Tasks Completed | 5 | 4 | -1 |
| Critical Tasks Delayed | 1 (Development) | 1 | Same |

5. Critical Path Analysis

Critical Path (Planned):

Requirement Analysis → Feasibility Study → Design → Development → Testing → Deployment

Current Path (Actual):

Requirement Analysis → Feasibility Study → Design → Database Setup → Development (Delayed)

6. Resource Assignment & Status

| Resource Name | Role | Assigned Task(s) | Current Status | Utilization (%) |
| --- | --- | --- | --- | --- |
| R1 – Project Manager | Planning & Monitoring | All Tasks | Active | 80% |
| R2 – System Analyst | Requirement, Feasibility | T1, T2 | Completed | 100% |
| R3 – UI/UX Designer | Design | T3 | Completed | 100% |
| R4 – Developer | Coding, Integration | T5, T6 | Ongoing | 70% |
| R5 – Database Admin | DB Setup | T4 | Completed | 100% |
| R6 – Tester | Testing | T6 | Not Started | 0% |
| R7 – Trainer | Deployment, Training | T7 | Not Started | 0% |
| R8 – Documentation Staff | Docs | T8 | Not Started | 0% |

7. Variance Summary

| Type | Observation | Impact |
| --- | --- | --- |
| Schedule Variance | Development task delayed by 5–6 days | Testing start delayed |
| Cost Variance | Minor increase in developer hours | Slight cost overrun |
| Performance Variance | Milestones M4 & M5 delayed | Project finish pushed ~1 week |
| Resource Variance | Uneven utilization (developer overloaded) | Requires redistribution |

8. Monitoring Actions and Recommendations

| Action | Responsible | Due Date | Goal |
| --- | --- | --- | --- |
| Accelerate Development | Developer Lead | 25 Dec 2025 | Meet Testing Start Date |
| Reassign Backup Developer | Project Manager | 22 Dec 2025 | Reduce Developer Overload |
| Prepare Test Cases in Parallel | Tester | 24 Dec 2025 | Reduce idle time |
| Daily Progress Review | Project Manager | Ongoing | Maintain 80–90% tracking accuracy |
| Update Baseline | PMO | 31 Dec 2025 | Adjust critical path |

9. Conclusion

  The First-Year Engineering Admission System project is currently 60% complete.

  The critical path is slightly delayed, mainly due to slower development.

  Corrective actions (adding developer & overlapping testing prep) are in progress.

  With effective monitoring and reallocation, the project can still finish by early February 2026.